## Draw Ledger
Bayfront Steel & Supply, LLC — Project Draw Ledger
Project: Berth 7 Reconstruction (Port Verano)
Subcontract No.: CMC-BSS-2025-0047
Invoice No. | Invoice Date | Description | Amount Billed | Amount Paid
INV-2025-0911 | 2025-09-15 | Mobilization + embedded steel Lot 1 | 62500.00 | 62500.00
INV-2025-1118 | 2025-11-18 | Structural steel Lot 2 delivery | 141000.00 | 141000.00
INV-2025-1220 | 2025-12-20 | Rebar Lot 3 delivery | 84600.00 | 55260.00
INV-2026-0214 | 2026-01-22 | Structural steel Lot 4 + rebar Lot 4 | 98400.00 | 0.00
INV-2026-0228 | 2026-02-26 | Final delivery + freight | 51015.00 | 0.00
|  | Totals | 437515.00 | 258760.00
|  | Gross balance billed less paid |  | 178755.00
|  | Less: 10% retainage held by GC |  | 48750.00
|  | Plus: retainage now earned/released |  | 48750.00
|  | Less: disputed Lot 4 rebar back-charge (rejected coils) |  | 18525.00
|  | Plus: approved freight true-up |  | 3585.00
|  | NET UNPAID BALANCE |  | 163815.00